## Slide 1
Implementing ‘Better Practice’ Permissions
A Playbook for regulators to streamline permissions and become digitally ready
Overview

## Slide 2
Overview
1
2
3
Three parts of the Playbook
Part A: defining your ambition for reform
This section is targeted at ‘Service Owners’ – regulatory leaders or senior managers responsible for permissions. It includes guidance to understand baseline practices and processes and define your parameters and ambition for reform.
Part B: designing better practice processes and delivering change
This section is targeted at ‘Reform officers’ – responsible for designing and implementing regulatory improvements. It includes guidance for designing better practice permissions and implementing reform.

## Slide 3: This Playbook was developed to help regulators improve administration of permissions
Regulators play a vital role in society ensuring fairness and safety across various sectors. They ensure that individuals and businesses comply with requirements under legislation and have powers to respond to non-compliance.
Permissions 1 are an important tool used by regulators to approve activities and manage risk. They exist alongside the broader regulatory tools used by regulators, such as education and engagement, compliance, monitoring and investigation activities.
Designing and administering permissions can be one of the most significant administrative activities for regulators. Applying for and processing permissions takes time and can be costly for both applicants and regulators.
It is important that regulators administer well targeted permissions in the most efficient and effective way possible. This helps regulated entities to operate and comply with regulations with the least burden.
This Playbook helps regulators to improve their regulatory practice and processes to achieve ‘better practice’ permissions and become more ‘digitally ready’.
Regulators and permissions play a vital role in society
This Playbook has been developed for ‘you’.
‘You’ may be a leader, manager, officer or specialist within a regulator tasked with improving permission practices and processes.
This Playbook will help you implement 'better practice’ permissions.
The Playbook outlines a repeatable approach to achieve ‘better practice’ permissions, enabled by digital reform.
You can work through the Playbook to review your end-to-end permission practice and process, or focus on specific parts.
You can use it as part of a significant reform program or through a continuous improvement approach.
1 Permissions includes licences, permits, registrations, authorisations, certifications and other related approvals. We refer to these as permissions throughout this report.

## Slide 4: It outlines a repeatable approach for regulators to achieve ‘better practice’ permissions and enable future digital reform
This Playbook was developed by Better Regulation Victoria (BRV) in partnership with four Victorian small regulators, Service Victoria and the Department of Treasury and Finance (DTF) through a collaborative co-design process.
While it was co-designed with small regulators, it is intended to be able to be used by all regulators across different permission schemes.
You are administering permissions in a more efficient and effective way, accounting for your overall approach to regulation and managing risks.
Implementing ‘better practice’ means:
You have a clear and risk-proportionate basis for permission requirements.
You have streamlined processes that are ‘user centric’ and help applicants and permission holders.
You have improved your processes so they are more efficient, effective and transparent.
‘Digital readiness’ could mean preparing to digitise the entire process, or digitising components of the process.
‘Digital readiness’ means:
You have done what you can with existing resources to prepare for future digitisation.
You have defined needs and a clear action plan that includes appropriate documentation to achieving future digital transformation in a way that is ready to engage with service providers.
WHAT DOES IT MEAN TO IMPLEMENT ‘BETTER PRACTICE’?
WHAT DOES IT MEAN TO BE ‘DIGITALLY READY’?
How were ‘better practice’ permissions designed?
Implement ‘better practice’ permission practices and processes
Become ‘digitally ready’, with a pathway for digital reform
The playbook is designed to help you achieve two things
1
2

## Slide 5: Implementing ‘better practice’ permissions have clear benefits
Better practice permissions result in an improved experience for applicants and permission holders and increased efficiencies and enhanced transparency for regulators and the Victorian Government. It can benefit regulators and regulated entities in many ways, reducing the administrative burden of permissions and enabling more effective regulation.
Improved applicant and permission holder experience, with better engagement and sentiment towards regulators
Streamlined interactions and shorter wait times, saving time and money
Greater confidence in applications, with a higher rate of quality applications
Fewer requests for further information (RFIs)
Less paperwork
BENEFITS FOR REGULATED ENTITIES
Improved employee experience, with officers better supported to process permissions
Fewer enquiries through phone-calls and emails and requests for further information (RFIs)
More efficient internal workflows and processes, enabled by effective digitisation
Better allocation of resources, aligned to risk
Greater transparency in decision making
More effective integration with other regulatory functions
Responsibly administering the relevant law
BENEFITS FOR YOU
Why should you implement ‘better practice’ permissions?

## Slide 6: Digital reform can enhance regulatory outcomes
Digitising permissions can assist Victorian regulators by improving information quality while enabling data-driven decision making and greater regulatory oversight. When done well, digital reform is one of the strongest levers to reduce burden on regulated entities and enhance regulatory outcomes. Digitisation should be reform-led, with processes improved in line with 'better practice’.
Improved and more accessible digital experience
Faster applications and regulatory interactions
Greater transparency and predictability, including progress and status of applications
Reuse of information where valuable
Fewer unnecessary questions with better and more dynamic applications
Less paperwork
BENEFITS FOR REGULATED ENTITIES
More efficient and transparent processing, with less manual effort
More automatically validated, reviewed and assessed information
Greater consistency in information and processes across applications
Better monitoring and reporting using data to identify trends and areas for improvement, securely stored and well organised
More effective integration between internal systems (front and back-end) and with external systems
Fewer human errors and inconsistencies
BENEFITS FOR YOU
Why should you digitise your permissions?

## Slide 7
This Playbook exists within the context of other regulatory reform work
This Playbook exists within the context of other Victorian Government frameworks and principles guiding ‘better practice’ permissions. It operationalises many of these frameworks and principles. You should refer to these resources when considering the broader design or role of permissions.
This playbook supports and enables other policies and reform across DTF, BRV and Service Victoria
Playbook for implementing permissions
Victorian Guide to Regulation
Service Victoria and digital reform
Victorian Permissions
Framework
Guide to assessing and designing permissions
Guide to operational design and management of permissions
Whole of organisation performance: 10 principles to support regulators in their journey towards best practice.
Towards Best Practice Guide
Victorian Permissions Framework | The role, design and administration of permissions: A framework to create or improve permissions, including as part of routine reviews of legislation and regulation.
Digital reform | The digitisation of permissions: Platforms and capabilities to digitise permissions, including through Service Victoria.
Playbook | The implementation of permissions: This Playbook, to implement ‘better practice’ permissions enabled by digital reform.
Guides | The design and assessment of permissions: Guidance and criteria for the design, assessment and management of permissions.
Victorian Guide to Regulation | The overarching policy guiding regulatory approaches: Guidance to determine and assess regulatory approaches when making regulations, including permissions.

## Slide 8: The Playbook is a ‘how to’ guide to implement ‘better practice’ permissions
HOW
USERS AND USE CASES
OUTPUT
This Playbook outlines a repeatable approach through a ‘how to’ guide to implement improvements to regulatory practice and processes to be more consistent, streamlined and digital.
It will take you through a four-step process to baseline your understanding, define your parameters and ambition, design ‘better practice’ processes and develop an action plan and related outputs to streamline the administration of your permissions.
Through this playbook, you can develop a set of actions and plan to implement improved permission practice processes that are ‘better practice’ and enable future digital reform. This will identify different outputs to develop to enable digitisation (e.g., procedures, system requirements, procurement).
You will be able to use this Playbook through different reform contexts including:
To assess how ‘digitally ready’ your practice and processes currently are
To prepare for future digital reform and implement improved practice and processes
To periodically or routinely review regulatory practice and process
To implement new permissions that are ‘better practice’ and digital
Understand your baseline process and practice
BASELINE
Define your parameters and ambitions
DEFINE
Design ‘better practice’ processes
DESIGN
Identify and implement improvements
IMPLEMENT

## Slide 9: Use this Playbook to develop an action plan for practice and process improvements and digital reform
Understand your baseline process and practice
Gather baseline information on your current state practice and processes and identify pain points and challenges across the permission journey.
Define your parameters and ambitions
Understand your ambitions and constraints for reform. Identify your parameters for digital and non-digital improvements, guided by frameworks and criteria.
BASELINE
DEFINE
Design ‘better practice’ processes
Work through the ‘better practice’ permission journey and use it to design an improved permission process.
Consider your requirements for digital reform, including through Service Victoria.
Identify and implement improvements
Conduct an in-depth review of key stages and components to identify improvements.
Document and prioritise opportunities, actions, and enablers for reform and digitisation, developing an action plan.
DESIGN
IMPLEMENT
Primarily for Service Owners – you are a regulatory leader or senior manager responsible for administering the permission.
Primarily for Reform Officers – you are a reform officer or team member responsible for designing and implementing regulatory improvements.
PART A
PART B
Note: Going through this process might surface strategic questions related to the policy, role and design of your permission.
Refer to Page 9 for other resources to help you with these broader considerations.

## Slide 10: Glossary
TERM | DEFINITION
Applicant | An entity applying for a permission. This could be an individual, sole trader or company.
User | An individual who uses the regulator’s platforms or systems. This is a general term that can refer to an applicant, representative, permission holder or regulated entity. When applying for a permission through digital services, a user can be considered a ‘customer’ of government services.
Delegate | A role that that undertakes activities due to their expertise or position. This could include more senior regulator officers involved in more complex assessment or approval decisions or representatives with the authority to act on behalf of a business. Delegates can be either in a regulator or regulated entity.
Permission | The right to engage in specific activities or conduct specified actions as granted by a regulatory authority. This can take the form of a licence, registration, permit, or other approval administered by a regulatory authority.
Permission holder | The entity that holds a permission from a regulatory authority and can undertake activities as defined through the permission. This could be an individual, sole trader or company.
Regulated entity | A business or individual that holds a permission, and whose conduct and activity is regulated by the regulatory authority. Regulated entities are considered a duty holder.
Service owner | A role within the regulator, generally a more senior manager or leader, that is responsible for the improvement and administration of a permission and how it is experienced as a service by applicants.
Reform officer | A role within the regulator, generally an officer or manager, that is responsible for designing and implementing improvements to regulatory practices and permission process.